## Sheet1
British Orienteering
Event Organisation Basic Checklist – NGOC Version
BOF: 0 = Organiser; P = Planner; C = Controller/Adviser
NGOC: C = Computing; Eq = Equipment; FP = Fixtures/Permissions; RT = Registration; S = String;
V = Volunteer Coordinator |  | ; A-E – NGOC Checklist references
Normally handled by the team/system. Check/monitor only
May require you to do something, or optional
Stuff you need to do
Not relevent to normal club events
To do/check first | NGOC | Risk Assessment | NGOC | Volunteers | NGOC | Equipment | NGOC
Access | FP, A4 | Make start | B3 | Event teams | V | Check store | Eq
Registration with BOF | FP | Talk to C |  | Team leaders | V | What needed | Eq
Car Park and keys | A1,3,B8 | Finish | C9 | Numbers | C1 | Extras? | C3
Toilets |  | Countersigned | C9 | Shifts | C1 | Transport | Eq
Talk to C | A2 | Search Plan |  | Searchers | C1 | Make list | C3
Advertise
Info for flyer/website | NGOC | Communications | NGOC | Signs | NGOC | Car Park | NGOC
Website info | B10,C5 | Check if mobiles /radios will work | C3 | Existing? | Eq, C2 | Team | V, C1
Check with C before finalising | C5 | Share mobile nos | C3 | Needed? | C2 | Equipment | Eq
|  |  |  | Where? | C2 | CP charge? | A1,A4
|  |  |  | How many? | C2 | Forest key | B8
|  |  |  | Whose job? | C2
Registration | NGOC | Start | NGOC | In the Forest | NGOC | Finish | NGOC
Shelter | Eq | Route to start | D10 | 2nd maps? |  | Equipment | Eq
Equipment | Eq | Equipment | Eq | Taped legs? | P | Manned? | C1
Recording names | RT | Maps | C4 | Rd crossings | P | Route back | P
Float | RT | Ctl descriptions | C4 | Drinks point(s) |  | Collection plan | P
E-card hire | RT | Any special info? | C4 | Patrols?
Info e.g. start, 1stAid | C4
Results/Download | NGOC | String Course | NGOC | Toilets | NGOC | Prize Giving | NGOC
Shelter | Eq | Suitable place | B5 | Location |  | What?
Equipment | Eq | Equipment | S | Hire? |  | How many?
Problems? | C | Signs | S | Delivery / collection |  | Where/When?
Runner check | C |  |  | Extra toilet rolls |  | Information
Complaints?
Traders | NGOC | First Aid | NGOC | Drinks | NGOC | Protests / Jury | NGOC
Plan in advance |  | Club or other? | V | Yes/No? |  | Required?
Litter? |  | Nearest A&E location/map | B3 | Water available? |  | Talk to C
|  | Info to competitors | C5 | Equipment |  | Have a plan
Litter
After event |  |  | NGOC | After event |  |  | NGOC
Results - OK with C? |  |  |  | Event accounts & money to club |  |  | RT
Club & British Orienteering website/rankings |  |  | C | Thanks letter/email to everyone involved
Numbers to British Orienteering |  |  | C, T | Incident form to BOF within 1 week |  |  | E7
Return equipment |  |  | Eq | Any learning points to club |  |  | E5
Reports 0 and C and expenses for officials |  |  | E6